## URStreamSight
Municipality Analyst,Municipality Leader | Municipality Analyst,Municipality Leader | Municipality Analyst
Login | Neighbourhood Recycling Data | Reporting |  | Machine Learning
Login and Authenticate | Neighbourhood Overview Data | Aggregate Data of Recycled Items and Contaminants | Problem Neighbourhood Information | Track Items in the Hopper | Identify items and contaminants
Release 0.1 MVP
Compile requirements and notes | Complete Business Case and Project Charter | Document Problem Definition
Create Milestone Schedule | Complete Risk Analysis, Stakeholder Analysis
Release 0.2 MVP
Lofi prototype of web app | Research Architecture | Develop Empathy Maps for stake holders
Gather additional requirements | Adjust Project definition
Release 0.3 MVP
Hifi prototype of web app | Update Problem Definition | Outline CICD pipeline
Continue Architecture Research | Define coding standards and guidelines
Release 1 MVP
Update USM | Research available libraries | Add Reporting Page | Add Additional Report
Setup CICD for front end | Add Recycling Overview Page
Create Web App Project
Install necessary libraries
Release 2 MVP
Create API Endpoints | Add Zoom Function | Add Aggregate Recycling Data | Add Problem Neighbourhood information
Update CICD pipeline
Release 3 MVP (Christmas Break)
Research Potential Frameworks | Create Database Schema | Research Testing plan Options
Implement NestJS Framework | Tie in API calls and database storage
Add additional API endpoints | Start to add RBAC
Release 4 MVP (Feb 4)
Review API Implementation | Finish RBAC implementation | Verify Database seeding
Add additional API Endpoints | Add basic tests
Release 5 MVP (Feb 25)
Add API calls to Frontend | Create documentation for new front end pages | Add basic heat map of contaminant disposal
Research Front end Integrations
Release 6 MVP (Mar 4)
Add Login Functionality | Add Testing to CICD Pipeline | Add Test Coverage to CICD Pipeline
Add Test and Staging server to CICD pipeline | Implement Testing Plan | Add additional API calls in front end
Release 7 MVP
Add Login Page | Add tool tip on hover | Add Export Function | Add Column Hiding