## URStreamSight
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
Login | Login and Authenticate | Compile requirements and notes |  | Done |  | Release 0.1 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Create Milestone Schedule |  | Done |  | Release 0.1 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Lofi prototype of web app |  | Done |  | Release 0.2 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Gather additional requirements |  | Done |  | Release 0.2 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Hifi prototype of web app |  | Done |  | Release 0.3 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Continue Architecture Research |  | Done |  | Release 0.3 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Update USM |  | Done |  | Release 1 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Setup CICD for front end |  | Done |  | Release 1 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Create Web App Project |  | Done |  | Release 1 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Install necessary libraries |  | Done |  | Release 1 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Create API Endpoints |  | Done |  | Release 2 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Update CICD pipeline |  | Done |  | Release 2 MVP | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Research Potential Frameworks |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Implement NestJS Framework |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Add additional API endpoints |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Review API Implementation |  | Done |  | Release 4 MVP (Feb 4) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Add additional API Endpoints |  | Done |  | Release 4 MVP (Feb 4) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Add API calls to Frontend |  | Done |  | Release 5 MVP (Feb 25) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Research Front end Integrations |  | Done |  | Release 5 MVP (Feb 25) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Add Login Functionality |  | Todo |  | Release 6 MVP (Mar 4) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Add Test and Staging server to CICD pipeline |  | Todo |  | Release 6 MVP (Mar 4) | Municipality Analyst Municipality Leader
Login | Login and Authenticate | Add Login Page |  | Todo |  | Release 7 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Complete Business Case and Project Charter |  | Done |  | Release 0.1 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Complete Risk Analysis, Stakeholder Analysis |  | Done |  | Release 0.1 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Research Architecture |  | Done |  | Release 0.2 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Adjust Project definition |  | Done |  | Release 0.2 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Update Problem Definition |  | Done |  | Release 0.3 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Define coding standards and guidelines |  | Done |  | Release 0.3 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Research available libraries |  | Done |  | Release 1 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Add Recycling Overview Page |  | Done |  | Release 1 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Add Zoom Function |  | Done |  | Release 2 MVP | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Create Database Schema |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Tie in API calls and database storage |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Start to add RBAC |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Finish RBAC implementation |  | Done |  | Release 4 MVP (Feb 4) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Add basic tests |  | Done |  | Release 4 MVP (Feb 4) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Create documentation for new front end pages |  | Doing |  | Release 5 MVP (Feb 25) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Add Testing to CICD Pipeline |  | Todo |  | Release 6 MVP (Mar 4) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Implement Testing Plan |  | Todo |  | Release 6 MVP (Mar 4) | Municipality Analyst Municipality Leader
Neighbourhood Recycling Data | Neighbourhood Overview Data | Add tool tip on hover |  | Todo |  | Release 7 MVP | Municipality Analyst Municipality Leader
Reporting | Aggregate Data of Recycled Items and Contaminants | Document Problem Definition |  | Done |  | Release 0.1 MVP | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Develop Empathy Maps for stake holders |  | Done |  | Release 0.2 MVP | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Outline CICD pipeline |  | Done |  | Release 0.3 MVP | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Add Reporting Page |  | Done |  | Release 1 MVP | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Add Aggregate Recycling Data |  | Done |  | Release 2 MVP | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Research Testing plan Options |  | Done |  | Release 3 MVP (Christmas Break) | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Verify Database seeding |  | Done |  | Release 4 MVP (Feb 4) | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Add basic heat map of contaminant disposal |  | Done |  | Release 5 MVP (Feb 25) | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Add Test Coverage to CICD Pipeline |  | Todo |  | Release 6 MVP (Mar 4) | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Add additional API calls in front end |  | Todo |  | Release 6 MVP (Mar 4) | Municipality Analyst
Reporting | Aggregate Data of Recycled Items and Contaminants | Add Export Function |  | Todo |  | Release 7 MVP | Municipality Analyst
Reporting | Problem Neighbourhood Information | Add Additional Report |  | Done |  | Release 1 MVP | Municipality Analyst
Reporting | Problem Neighbourhood Information | Add Problem Neighbourhood information |  | Done |  | Release 2 MVP | Municipality Analyst
Reporting | Problem Neighbourhood Information | Add Column Hiding |  | Todo |  | Release 7 MVP | Municipality Analyst
Machine Learning | Track Items in the Hopper
Machine Learning | Identify items and contaminants
Note on B2: As a User, I want a login page so that I can access private data securely.
Note on B24: As a User, I want to be able to view data so that I can have a quick overview of current recycling in the municipality.
Note on B42: As a Municipality Analyst, I want an aggregate view of contaminants so that I can view the most common contaminants easily to make informed decisions.
Note on B53: As a Municipality Analyst, I want to be able to compare neighbourhoods and areas in the municipality so that I can determine areas of concern.

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Release 0.1 MVP |  | 9/14/2020 12:00:00 AM | 10/5/2020 12:00:00 AM | True | False
Release 0.2 MVP |  | 10/5/2020 12:00:00 AM | 11/2/2020 12:00:00 AM | True | False
Release 0.3 MVP |  | 11/2/2020 12:00:00 AM | 11/16/2020 12:00:00 AM | True | False
Release 1 MVP |  | 11/16/2020 12:00:00 AM | 11/30/2020 12:00:00 AM | False | False
Release 2 MVP |  | 11/30/2020 12:00:00 AM | 12/14/2020 12:00:00 AM | True | False
Release 3 MVP (Christmas Break) |  | 12/14/2020 12:00:00 AM | 1/21/2021 12:00:00 AM | True | False
Release 4 MVP (Feb 4) |  | 1/21/2021 12:00:00 AM | 2/4/2021 12:00:00 AM | True | False
Release 5 MVP (Feb 25) |  | 2/5/2021 12:00:00 AM | 2/25/2021 12:00:00 AM | True | False
Release 6 MVP (Mar 4) |  | 2/4/2021 12:00:00 AM |  | False | False
Release 7 MVP |  |  |  | False | False

## Personas
Persona | Group | Details | Picture
Municipality Leader | User | Municipality Leader interested in general overview of data. | 0
Municipality Analyst | User | Analyst user at the municipality using our software, uses data to make decisions. | 0