## URStreamSight
Municipality Analyst,Municipality Leader | Municipality Analyst,Municipality Leader | Municipality Analyst
Login | Neighbourhood Recycling Data | Reporting
Login and Authenticate | Neighbourhood Overview Data | Aggregate Data of Recycled Items and Contaminants | Problem Neighbourhood Information
Release 0.1 MVP
Compile requirements and notes | Complete Business Case and Project Charter | Document Problem Definition
Create Milestone Schedule | Complete Risk Analysis, Stakeholder Analysis
Release 0.2 MVP
Lofi prototype of web app | Research Architecture | Develop Empathy Maps for stake holders
Gather additional requirements | Adjust Project definition
Release 0.3 MVP
Hifi prototype of web app | Update Problem Definition | Outline CICD pipeline
Continue Architecture Research | Define coding standards and guidelines
Release 1 MVP
Update USM | Research available libraries | Add Reporting Page | Add Additional Report
Setup CICD for front end | Add Recycling Overview Page
Create Web App Project
Install necessary libraries
Release 2 MVP
Add Login Page | Add heat map of contaminant disposal | Add Aggregate Recycling Data | Add Problem Neighbourhood information
Create API Endpoints
Tie in API calls and database storage
Update CICD pipeline
Release 3 MVP
Add additional API endpoints | Add Zoom Function | Add Export Function | Add Column Hiding
Add Login Functionality | Add tool tip on hover
Release 4 Future Release MVP
Add Test and Staging server to CICD pipeline